## Re-Entry after COVID-19
Task Name | Duration | Start | Finish | Predecessors | Assigned To | % Complete | Status | Comments
Planning for occupancy
Develop a new operating model / operational goals
Determine Re-entry Team (Oversight Committee)
Identify Organizational Stakeholders
Develop Roles and Responsibilities Matrix
Set up meeting/communication schedule
Develop an occupancy transition schedule with the critical path identified
Design the project team structure for implementing operational readiness program
Identify roles & responsibilities and develop a RASCI matrix
Develop a Communicate Plan to convey expected behaviors and protocols to returning staff and other stakeholders (customers, visitors, etc.)
Develop Program phasing and milestone plan
Update the Business Continuity / Emergency Response Plan
Establish risk tolerance (consider decision tree) for each phase/milestone
Develop a Contingency Plan
Develop a Program Management Plan (projects required and associated costs and tradeoff)
Develop an Operational readiness budget
Secure funding commitment
Develop a phased staffing plan for employee re-entry to align with new operating model and occupancy transition schedule
Prioritized employee phasing plan for re-entry
Prioritized functional space phasing plan
Prioritized building services plan
FM staffing plan (to support phased staffing and space plans)
Update Occupational Health & Safety Policies
Review and update compliance with industry and local mandates
Develop Staff Wellness SOPs
Develop internal corporate policies for employee support/protection
Develop employee cleaning/disinfecting/distancing requirements
Develop training plan and schedule
Conduct employee training
Develop signage plan for new policies and wayfinding needs
Develop a communication plan and messaging approach
Identify target audience groups
Identify delivery channels for each target group
Develop custom messaging for the target audiences
Develop a communication schedule aligning with the phased staffing plan
Develop criteria to measure effectiveness of communication
Develop a Site Management Plan
Update the Corporate Sourcing Strategy
Develop a Contractor and Vendor Management Plan
Update the Pest Management Plan
Update the Supply Chain Management Plan and availability of materials/resources
Pre-occupancy
Update Safety Protocols
Update Indoor Environmental Control Plan
Restart Building Systems
Validate Water Quality
Validate indoor air quality
Update shutdown/restart procedures
Update access and security requirements
Update Visitor access requirements
Review and update operating plans to align with new operating model and phased re-entry plan
Security
Health and safety
PPE requirements
Traffic patterns and traffic flow
Communication systems
Cleaning Program
Cleaning Contract Management
Develop Levels of Service for Cleaning
Establish level of sanitation required for each space
Establish frequencies for each space
Review and update Standards/Protocols
Develop a Monitoring program
Develop an issue reporting and resolution plan
Security
Physical safety elements
Procedures, protocols and plans
During occupancy
Review and update the FM plan
Space utilization
Facility capacity and alternative workplace programs
Planning for future staffing accommodations (next wave of re-entry or reductions)
Planning for future functional needs (Meeting rooms, food facilities, conference facilities)
Review and Update Change Management Plan
Review and update operational staffing plans
Maintenance staffing plan update
Janitorial staffing plan update
Security staffing plan update
Review and Update O&M Program
Emergency Budget review
New technologies review to automate safety needs
Develop thresholds for allowable Deferred Maintenance
Prioritize and Review Preventive Maintenance Schedule to accommodate manpower changes
Review and update Warranty Management Plan
Evaluate modifying consumable inventory
Evaluate and inventory critical spare parts
Review priority of Critical Systems
Review and update O&M policies to align with the new operating model
Update Emergency Preparedness/Business Continuity plans
Review predictive data analytics and develop response plan
Monitor and update risk mitigation and contingency plan
Monitor and influence occupant behavior
Short-term
Update the FM plan for the new operating model
Update the Space Plan incorporating planned phased re-entry
Update the staffing plan incorporating the new operating model and skills transition planning
Update the O&M plan
Develop strategy for new technology/sterile environments needs (No-touch doors and bathroom accessories)
Perform Policy Reviews
Prioritize and develop a matrix for Interaction requirements with other departments
Develop rapid response closure plan to support contingency planning incorporating lessons learned
Monitor and influence occupant behavior
Long-term
Redefine the new workplace
Evaluate the efficiencies of remote teleworking
Plan for the long term phased full re-occupancy
Prioritize long-term organizational needs
Prioritize long-term functional space
Evaluate long-term real estate needs (acquire more space/dispose of unused space)
Develop phased budget for long-term staffing and space needs

## Comments
Row 60 | Not just space? Equipment? transport systems? is there another word? | Vicky Acosta | 04/29/20 11:05 PM
Row 65 | New | Vicky Acosta | 04/29/20 11:08 PM